## Slide 1: Eastside Sewage Transfer Scheme (ESTS) Phase 4
Ministry of Transport – Press Call
Transport Road Section

## Slide 2
ESTS - Overview

## Slide 3
ESTS - Overview
What is the ESTS?
• A new 3.8 km long, twin pumping main designed to safely carry sewage from the sewage pumping station in Eastside Kingsway roundabout area up to the main trunk sewer at Rosia Parade in the south.
• The route involves a combination of buried pipelines along roads and surface mounted pipelines running inside ex-MOD tunnels (Admiralty North-South and Admiralty East-West tunnels).
• The system consists of twin pipes of 450mm and a 355mm diameter respectively.
• Four additional pumps will be installed to cope with future sewage flows
As part of ESTS – Phase 6
To date – Over 100m of the 875m has been laid in Phase 1 (Eastside)

## Slide 4
ESTS - Overview
450mm
355mm
Pumping Station

## Slide 5
ESTS PHASE 4 – Key Details
ESTS - Phase 4
  Divided into 8 smaller stages.
  Total of 808m of dual pipes (355mm & 450mm) for Phase 4.
  From Saluting Battery (exercise park)  Rosia Road  Transport Road down South Pavilion Rd discharging at Rosia Parade.
Contractor = GJBS
  £1.88m contract
  Entire duration of Phase 4 = 1 year
Start on site = Sat 4th October 2025
Transport Road Section (ESTS Phase 4)
Duration of this phase of works = 12 Weeks
Total length of pipe for this section = 98m
Avg excavation depth 2.4m
Avg trench width 2m

## Slide 6
Impacts of Phase 4 – Transport Road
Traffic Flow
Parking
Bus Routes

## Slide 7
Impacts of Phase 4 – Transport Road
Traffic Flow
Traffic coming down South Pavilion Road will continue down to Rosia Road and Rosia Bay.
Traffic coming up Cumberland Road will not be able to continue towards Rosia Bay.
Traffic coming from Nelson’s View and Rosia Bay Area will not be able to go up South Pavilion Road and will be diverted along Rosia Road.
CLOSED REVERSE FLOW UNCHANGED

## Slide 9
Impacts of Phase 4 – Transport Road
Traffic Flow – Both Worlds Traffic Lights
Both Worlds traffic light signals will be reduced in length (old winter schedule) to improve the bus route and schedule timings. Strictly no parking will be allowed on Sir Herbert Miles Road. The parking spaces will return for the 2026 summer season.

## Slide 10
Impacts of Phase 4 – Transport Road
Traffic Flow
Parking
Bus Routes

## Slide 11
Impacts of Phase 4 – Transport Road
Parking
Parking will temporarily lost for the duration of the works at;
Transport Road.
Parking Bays on Rosia Road (opposite Cumberland Road)
5 Parking spaces in front of Bayview and Clock Tower (for temporary bus shelter)

## Slide 12
Impacts of Phase 4 – Transport Road
Parking
Due to change in traffic flow direction, parked vehicle orientation needs to be corrected.
On 4th October, temporary parking restrictions will be put in place in these areas to allow for implementation of new traffic flow and allow vehicles to park in the correct direction.
The restrictions in these areas will be for a number of hours on the 4th October and will be removed as soon as all vehicles are cleared.

## Slide 13
Impacts of Phase 4 – Transport Road
Traffic Flow
TEMPORARY PARKING LOSS
REORIENTATED PARKINGS

## Slide 14
Impacts of Phase 4 – Transport Road
Traffic Flow
Parking
Bus Routes

## Slide 15
Impacts of Phase 4 – Transport Road
Bus Routes
Temporary bus stop at Bay View Terraces (Rosia Road).
Temporary bus stop at Rosia Plaza.
Suspension of route 4.
Changes to Route 3, 8 and 9.
Improved frequency of buses on route 8 and 9.

## Slide 16
ROUTE 3
ROUTE 9
BUS STOP
Bayview (Temp)
Impacts of Phase 4 – Transport Road
Bus Routes
Rosia Plaza (Temp)
New Mole House
ROUTE 3
ROUTE 9
BUS STOP

## Slide 17
Impacts of Phase 4 – Transport Road
Bus Routes

## Slide 18
Impacts of Phase 4 – Transport Road
New Bus Timings
Buses leave Both Worlds every 15 minutes due to removal route 4
OLD
NEW

## Slide 19
Impacts of Phase 4 – Transport Road
New Bus Timings
Buses leave Bayview every 20 minutes due to removal of route 4
OLD
NEW